## Project Summary
Project Name | Report Date | Team Members | Project Overview | Current Status
Cleaning Service Booking System | 2026-08-31 | Faith, Ntando, Rais | A system that allows users to book cleaning services, track availability, and manage cutomer information, give reports. | On Track

## Task Tracking
Task | Description | Assigned To | % Complete | Start Date | Due Date | Status | Notes
Github repository setup |  | uzair | 100% | 2026-08-03 | 2026-08-05 | Done
Jira board setup |  | yaaseen | 100% | 2026-08-03 | 2026-08-04 | Done
SQL Database setup | Run Schema & Seed scripts | yaseen, uzair | 100% | 2026-08-04 | 2026-08-05 | Done
Test system functionality | Exploritory testing | yaseen, uzair | 90% | 2026-08-05 | 2026-08-07 | Done
Task allocation | Allocate tasks on Jira | yaseen, uzair | 100% | 2026-08-05 | 2026-08-10 | Done
API (Swagger) | Run api script | yaseen, uzair | 100% | 2026-08-03 | 2026-08-03 | Done
UI (Frontend) | Run UI script | yaseen, uzair | 100% | 2026-08-03 | 2026-08-03 | Done
Jira board task management | Create Epics, stories and subtasks | uzair | 90% | 2026-08-05 | 2026-09-03 | Done
Github repository management | Create READ.ME file, .gitignore etc. | uzair, yaseen | 100% | 2026-08-06 | 2026-09-07 | Done
Authentication endpointg testing | POSTMAN APIs | uzair, yaaseen | 100% | 2026-08-07 | 2026-08-18 | Done
Database Diagram | Create database diagram to show relations | uzair | 100% | 2026-08-10 | 2026-08-10 | Done
Stock and Inventory | Inventory fetches, stock updates, etc. | uzair | 90% | 2026-08-11 | 2026-09-04 | Done
Credit and debt governance | Transactions triggered by expired credit terms or exhausted limits | yaaseen | 90% | 2026-08-11 | 2026-09-04 | Done
cypress setup | download, setup and testrun | uzair | 100% | 2026-08-12 | 2026-08-25 | Done
Troubleshooting errors |  | uzair, yaseen | 100% | 2026-08-14 | 2026-08-25 | Done
stock and inventory testing | get requests | uzair | 90% | 2026-08-17 | 2026-08-25 | Done
credit nad debt governance tetsing | credit validity | yaaseen | 90% | 2026-08-17 | 2026-08-31 | Done
Pricing & revenue integrity | VAT | uzair, yaseen | 90% | 2026-08-18 | 2026-08-31 | Done
SQL Validation scripts Group 1 | Stock Reconciliation | uzair | 90% | 2026-08-22 | 2026-08-31 | Done
SQL Validation scripts Group 2 | Pricing Audit | uzair | 90% | 2026-08-22 | 2026-08-31 | Done
SQL Validation scripts Group 3 | Data hygiene and constraints | yaaseen | 90% | 2026-08-22 | 2026-08-31 | Done
SQL Validation scripts Group 4 | Business Intelleigience reports | yaaseen | 90% | 2026-08-22 | 2026-08-31 | Done
Jira Board | inserting descriptions & evidence into subtasks | yaaseen, uzair | 100% | 2026-08-26 | 2026-09-05 | Done
Defect logging | Compiling evidence | uzair, yaaseen | 100% | 2026-08-29 | 2026-09-05 | Done
Presentation Prep |  | uzair,yaaseen | 80% | 2026-08-31 |  | in progress

## Outstanding Tasks
Issue / Task | Assigned To | Priority | Due Date | Status | Comments

## Risks & Blockers
Risk / Blocker | Impact | Likelihood | Mitigation Plan | Owner | Status